## high-level-marketing
High Level Marketing Budget
Q4 2021
Name | Subitems | Goal | Priority | Type | Budget | Actual | Remaining Budget | Status | Timeline - Start | Timeline - End
Planning | Retrospect the Existing Design, Plan the Resourcing and Project Plan, Resource Onboarding | Successfully complete Business Requirements Gathering and Complete the proper planning phase | High | Planning | 2000 | 1600 | 400 | Completed | 2021-10-04 | 2021-10-27
Subitems | Name | Status
| Retrospect the Existing Design | Done
| Plan the Resourcing and Project Plan | Done
| Resource Onboarding | Done
Analyze | Analyze the Design, Budget Analysis, Resource Analysis | Analyze the Risk factors and the project repurcussions | Medium | Analyze | 1000 | 1250 | -250 | Completed | 2020-10-25 | 2020-11-10
Subitems | Name | Status
| Analyze the Design | Done
| Budget Analysis | Done
| Resource Analysis | Done
Design | Design the Environment, Design the Project landscape, Plan and break the project into sprints | Successfully complete the Design phase | Medium | Design | 5000 | 4350 | 650 | Completed | 2020-11-08 | 2020-12-08
Subitems | Name | Status
| Design the Environment | Done
| Design the Project landscape | Done
| Plan and break the project into sprints | Done
Implementation | Start with the Initial Sprint, Implement the Technical business requirements, Implement the Functional Business requirements | Successfully complete the Implementation of the project as per the Business and Functional Requirements | Medium | Implementation | 5500 | 5600 | -100 | Completed | 2021-12-09 | 2021-12-31
Subitems | Name | Status
| Start with the Initial Sprint | Done
| Implement the Technical business requirements | Done
| Implement the Functional Business requirements | Done
[5 empty] | 13500 | 12800 | 700 |  | 2020-10-25 | 2021-12-31
Q1 2022
Name | Subitems | Goal | Priority | Type | Budget | Actual | Remaining Budget | Status | Timeline - Start | Timeline - End
Implementation | Perform any enhancements required, Retrospect the implementations | Successfully complete the Implementation of the project as per the Business and Functional Requirements | Medium | Implementation | 2500 | 3400 | -900 | Completed | 2021-01-01 | 2021-01-19
Subitems | Name | Status
| Perform any enhancements required | Done
| Retrospect the implementations | Done
Testing | Test the technical requirements, Test the functional requiremts | Successfully perform Testing for the implemented | Medium | Testing | 3000 | 2750 | 250 | Working on it | 2021-01-17 | 2021-02-02
Subitems | Name | Status
| Test the technical requirements | Working on it
| Test the functional requiremts | Working on it
Go -live | Go - Live | Go Live, Retrospection, Bug Fixes and Upgrade Patches | High | Go Live |  |  | 0 | Running/Live | 2022-02-01 | 2022-02-28
[5 empty] | 5500 | 6150 | -650 |  | 2021-01-01 | 2022-02-28

## Visualization
Type | DAYS | Timeline - Start | Timeline - End | Status | Tasks | Type | Actuls | Budgets
Planning | 23 | 2021-10-04 | 2021-10-27 | Done | 14 | Planning | 2000 | 1600
Analyze | 16 | 2020-10-25 | 2020-11-10 | Working on it | 2 | Analyze | 1000 | 1250
Design | 30 | 2020-11-08 | 2020-12-08 | Running/Live | 1 | Design | 5000 | 4350
Implementation | 41 | 2021-12-09 | 2022-01-19 |  |  | Implementation | 8000 | 9000
Testing | 16 | 2022-01-17 | 2022-02-02 |  |  | Testing | 3000 | 2750
Go Live | 27 | 2022-02-01 | 2022-02-28
Actuals |  |  |  | Budgets |  |  |  | Remaining Budget
18950 |  |  |  | 19000 |  |  |  | 50